## ProJect Plan (Gantt Chart )
Project Name: | Pharmacy Business Intelligence Dashboard
Start Date: | 2025-01-18
Cuurent Date: | 2025-04-17
Current Week: | 13
Milestone/Task | Task Lead | Start Date | End Date | Days | Progress | 2025-01-18 | 2025-01-21 | 2025-01-25 | 2025-01-28 | 2025-02-01 | 2025-02-04 | 2025-02-08 | 2025-02-11 | 2025-02-15 | 2025-02-18 | 2025-02-22 | 2025-02-25 | 2025-03-01 | 2025-03-04 | 2025-03-08 | 2025-03-11 | 2025-03-18 | 2025-03-21 | 2025-03-28 | 2025-03-31
| Project Lead |  |  |  |  | wk 1 | wk 1.5 | wk 2 | wk 2.5 | wk 3 | wk 3.5 | wk 4 | wk 4.5 | wk 5 | wk 5.5 | wk 6 | wk 6.5 | wk 7 | wk 7.5 | wk 8 | wk 8.5 | wk 9 | wk 9.5 | wk 10 | wk10.5
Project Initiation
Define objectives, scope, | Omar | 2025-01-18 | 2025-01-22 | 4 | 100%
Identify stakeholders and reporting needs | Dalia | 2025-01-19 | 2025-01-22 | 3 | 100%
Develop a project plan | Zain | 2025-01-20 | 2025-01-25 | 5 | 100%
Define KPIs | Asmaa | 2025-01-22 | 2025-01-24 | 2 | 100%
Data Setup & Connection
Develop Python script to connect Odoo to SQL | Sarah | 2025-01-18 | 2025-01-31 | 13 | 100%
Extract and store Odoo data into SQL | Omar | 2025-02-01 | 2025-02-06 | 5 | 100%
Automate incremental data updates | Asmaa | 2025-02-08 | 2025-02-12 | 4 | 100%
Test data consistency & error handling | Hagar | 2025-02-13 | 2025-02-13 | 0 | 100%
Data Processing
Write SQL queries for structuring and analysis | Asmaa | 2025-02-01 | 2025-02-06 | 5 | 100%
Identify new attributes and calculated fields | Zain | 2025-02-07 | 2025-02-11 | 4 | 100%
Optimize SQL queries for performance | Dalia | 2025-02-12 | 2025-02-16 | 4 | 100%
Data Cleaning
Connect Power BI to SQL | Sarah | 2025-02-12 | 2025-02-17 | 5 | 100%
Transform and clean data using Power Query | Omar | 2025-02-15 | 2025-02-20 | 5 | 100%
Handle missing values and format inconsistencies | Hager | 2025-02-21 | 2025-02-25 | 4 | 100%
Dashboard Development
Design dashboard layout and KPIs | Asmaa | 2025-02-23 | 2025-02-27 | 4 | 100%
Create interactive visualizations | Zain | 2025-02-28 | 2025-03-05 | 5 | 100%
Implement DAX calculations | Asmaa | 2025-03-01 | 2025-03-15 | 14 | 100%
Test dashboard performance | Dalia | 2025-03-11 | 2025-03-13 | 2 | 100%
Deployment & Handover
Deploy dashboard and schedule refresh | Omar | 2025-03-14 | 2025-03-19 | 5 | 100%
Train end-users | Hager | 2025-03-17 | 2025-03-22 | 5 | 20%
Create PDF documentation | Zain | 2025-03-20 | 2025-03-24 | 4 | 100%
Record video tutorial | Hager | 2025-03-20 | 2025-03-25 | 5 | 0%
Monitoring
Ensure Python script runs on schedule | Asmaa | 2025-03-25 | 2025-03-28 | 3 | 80%
Monitor Power BI refresh | Dalia | 2025-03-26 | 2025-03-29 | 3 | 80%
Optimize queries and dashboards | Hager | 2025-03-27 | 2025-03-30 | 3 | 10%
Project Presentation
Training all team on Presentaion | All Team Members | 2025-04-01 | 2025-04-08 | 7 | 100%
present the project | All Team Members | 2025-04-10 | 2025-04-11 | 1 | 0%

## Risk & Mittigation Plan
Risk Category | Risk Description | Potential Impact | Likelihood | Mitigation Strategy
Data Integrity & Security | Accidental data deletion while connecting Odoo to SQL via Python | Loss of critical pharmacy data. | High | Implement backups before sync, use a read-only user for initial testing, and log all operations.
Data Integrity & Security | Data inconsistency in Odoo (incorrect/missing fields) | Wrong insights in analysis. | High | Apply data validation rules before import and schedule regular data audits.
SQL & Data Processing | SQL database integrity issues (duplicates, missing records) | Data corruption. Incorrect reports. | Medium | Use Primary Keys, Constraints, and run ETL validation scripts.
SQL & Data Processing | Poor database indexing affects performance | Slow dashboard response. | High | Apply indexing strategies, optimize SQL queries, and use stored procedures where applicable.
Power BI Dashboard | Incorrect visualizations due to data mismatch | Misleading insights. | High | Validate reports against raw SQL data, conduct manual verification before release.
Project Timeline & Delivery | Couldn’t match project timeline | Delayed delivery. Missed deadlines. | High | Use agile sprints, set milestone checkpoints, and reallocate resources if needed. Prioritize critical tasks first.
Project Management Risks | Lack of documentation | Future maintenance issues. | Medium | Maintain a data flow diagram, system architecture docs, and process documentation.

## Dropdown lists (hidden)
Project Lead
Omar
Sarah
Asmaa
Dalia
Hager
Zain
All Team Members